## Current vs Target
Dimension | Current State | Target State (Year 3) | Gap Description | Gap Severity | Dependencies
Monthly Revenue | $0 | $100K+/mo | No revenue architecture | Critical | Market validation
Total Customers | 0 | 50+ enterprise | No customer base | Critical | Product-market fit
Products Deployed | 0 | 5+ products | Architecture only | Critical | MVP build
Trained Operators | 0 | 100+ | No talent pipeline | High | Operator Track launch
Enterprise Deployments | 0 | 5+ | No deployments | Critical | First paying client
Agent Systems Built | 0 (architecture) | 20+ production | Documents only | High | Technical build
Governance Infrastructure | Specified | Deployed | Not instantiated | High | Enterprise demand
Insurance Layer | Conceptual | Active (50+ cycles) | No empirical data | Medium | Phase 5+
Constitutional Framework | Documented | Ratified | Not instantiated | Low | Institutional scale
Cloud Infrastructure | None | Multi-region GKE | No deployment | High | First AINE launch
Data/Execution Telemetry | Zero | 10K+ decision traces | No data moat | High | Production usage
IP Portfolio | Unregistered | 10+ registered | No protection | Medium | Revenue threshold
Team Size | 1 (solo founder) | 50+ operators | Bottleneck | Critical | Revenue funds hiring
External Capital | $0 | Sustainable revenue | Bootstrap only | High | Revenue-first
Market Validation | 0 conversations | 200+ discovery calls | No buyer contact | Critical | Week 1 priority
Regulatory Positioning | None | IMDA reference partner | No engagement | Medium | Phase 4+
Case Studies | 0 | 10+ published | No credibility | High | First 3 clients
Website (frankmax.com) | Not launched | Active, converting | No web presence | High | Month 1
Legal Structure | Unincorporated | Registered entity | No legal basis | High | Month 1
Technology Stack | Not deployed | Production k8s | Nothing running | High | Week 3-4
ORF Protocol | Specified | MVP kernel (K1-K4) | Not built | Medium | Phase 3+
Frankmax PIAR | Designed | Deployed to 5+ clients | Not operational | High | Phase 3
Levelupmax Track | Designed | 3+ cohorts completed | Not launched | High | Month 4
DocuFlow Agent | Conceptual | 100+ paying users | Not built | Critical | Week 1-2
Billing Leakage Engine | Conceptual | 3+ enterprise clients | Not built | High | Month 2-3
Chokepoint Intelligence | Framework exists | 5+ sprints delivered | Not sold | Critical | Month 1
Insurance Claims Agent | Specified | 50K+ claims processed | Not built | Medium | Month 7+
Venture Cells | Designed | 10 active cells | None operating | High | Month 4+
WGE OpenClaw Runtime | Specified | Production runtime | Not deployed | Medium | Phase 3
Agent Marketplace | Conceptual | Beta with transactions | Not built | Low | Month 10+
Kill Discipline | Documented | 3+ ventures killed | Never tested | Critical | Year 1
PCI Enforcement | Designed | Active enforcement | Never tested | Medium | Year 2+
Death Protocol | Specified | Executed 5+ times | Never tested | High | Year 1
Cross-border Capability | Conceptual | 2+ jurisdictions | No deployment | Low | Phase 5+
Brand Authority | None | Industry recognition | Zero visibility | High | Case studies first
Promoter Network | None | 10+ active promoters | No distribution | Medium | Month 4+
UniVenture IP Stacks | 50+ designed | 5+ deployed | Not built | Low | Phase 4+
LPI Services | 23 specified | 1 pilot | Not built | Low | Phase 5+
Financial Model | Projected | Validated by actuals | Unvalidated | High | Month 3
Audit Infrastructure | Specified | Court-grade logging | Not deployed | Medium | Phase 3

## Phase Transitions
Phase# | Name | Duration(mo) | Entry Conditions | Exit Conditions | Kill Criteria | Monthly Rev Target | Cumulative Rev | Key Deliverables (top 5) | Resources | Capital Required | Primary Risk | Dependency | Success Prob%
1 | First Revenue | 3 | None | $10K+/mo revenue | No revenue by Day 90 | $5-15K | $5-15K | DocuFlow+Chokepoint+Website+Legal+First Client | Solo founder | $0 | No market need | None | 70
2 | Scale & Systemize | 3 | $10K/mo revenue | $30K+/mo, 3+ clients | Margin<35% by Month 6 | $15-30K | $20-45K | 100 users+Operator Track+Enterprise Client+Agent System | 1 founder+5 operators | $5K tools | Talent quality | Phase 1 revenue | 60
3 | Verticalize | 3 | $30K/mo, 3+ clients | $50K+/mo, vertical proven | Vertical underperforms horizontal | $30-50K | $50-95K | Insurance agent+Copilot+Governance layer | 10-20 operators | $10K infra | Enterprise sales cycle | Phase 2 clients | 55
4 | Platform | 3 | $50K/mo, vertical proven | $100K+/mo, marketplace beta | No network effects by Month 12 | $50-100K | $100-195K | Marketplace+Identity+Frankmax PIAR | 20-30 operators | $25K infra | Platform adoption | Phase 3 vertical | 45
5 | Cross-Industry | 12 | $100K/mo, 1 vertical | Multi-vertical, $200K/mo | Industries won't adopt shared layer | $100-200K | $300-395K | Cross-vertical agents+Coordination layer | 50+ operators | $50K | Coordination complexity | Phase 4 platform | 35
6 | Institutional | 12 | Multi-vertical | Government pilots | Regulatory blocks | $200-400K | $500-795K | Gov pilots+Regulatory endorsement+ORF MVP | 100+ operators | $100K | Regulatory friction | Phase 5 scale | 25
7 | Infrastructure | 24 | Government trust | Platform>product revenue | Better alternative emerges | $400K+ | $900K+ | Invisible infrastructure+Insurance layer | 200+ operators | $250K | Ecosystem competition | Phase 6 institutional | 20

## 90-Day Sprint
Week | Primary Objective | Secondary | Deliverables | Cumulative Rev($) | Cumulative Conversations | Cumulative Deals | Blocker Risk | Decision Required | Tool Needed | Success Metric | Status
1 | Register legal entity + Launch frankmax.com | Build prospect list | Entity+Website+150 prospects | 0 | 0 | 0 | Legal delays | Entity type | Domain+hosting | Website live | Not Started
2 | Start 20 discovery conversations | Build DocuFlow MVP skeleton | 20 outreach emails sent | 0 | 5 | 0 | Low response rate | Which vertical first | Email+CRM | 5 conversations booked | Not Started
3 | Complete 10 discovery calls, extract pain | DocuFlow v0.1 working | Pain map+DocuFlow prototype | 0 | 15 | 0 | Wrong vertical | Pivot or persist | Zoom+Notes | 10 calls completed | Not Started
4 | Send 3 proposals from discovery insights | DocuFlow beta with 3 test users | 3 proposals sent | 0 | 20 | 0 | Proposals rejected | Reprice or reposition | Proposal template | 3 proposals out | Not Started
5 | Close first deal | DocuFlow onboard 5 beta users | First signed contract | 5000 | 25 | 1 | Deal falls through | Discount or walk | Contract template | $5K+ in pipeline | Not Started
6 | Deliver first sprint/project | Iterate DocuFlow based on feedback | Sprint deliverable complete | 15000 | 30 | 1 | Delivery quality | Hire help or solo | Project tools | Client satisfied | Not Started
7 | Second deal from referral/pipeline | DocuFlow 10 users | Second contract signed | 20000 | 35 | 2 | Pipeline dry | Double outreach | Same | 2 paying clients | Not Started
8 | Third deal + start recurring retainer | Launch DocuFlow subscription | Third contract+first retainer | 30000 | 40 | 3 | Capacity limit | Prioritize | Billing system | $5K MRR | Not Started
9 | Deliver second sprint | Operator Track curriculum draft | Second deliverable done | 40000 | 45 | 3 | Quality variance | Standardize | Delivery templates | 2 clients retained | Not Started
10 | Fourth deal + Billing Leakage Engine pilot proposal | Begin recruiting first 5 operators | Fourth contract | 50000 | 50 | 4 | Solo capacity | Must recruit | Job posting | 4 deals total | Not Started
11 | Deliver third sprint + close Billing Leakage pilot | Operator screening (10 candidates) | Third deliverable+BLE proposal | 65000 | 55 | 5 | BLE data access | Client IT cooperation | Data connectors | BLE pilot signed | Not Started
12 | Systematize delivery process | Operator Track pilot (5 trainees) | Process playbook + training start | 75000 | 60 | 5 | Process doesn't scale | Simplify | Documentation | Repeatable process | Not Started
13 | Quarter review + Phase 2 planning | First operator-assisted delivery | Q1 report + Phase 2 plan | 85000 | 65 | 6 | Targets missed | Adjust Phase 2 | Analytics | Revenue>$15K/mo avg | Not Started

## Revenue Architecture
Stream | Buyer Persona | Price Point | Sales Cycle(days) | Capital to Build | Time to First$(days) | Recurring? | Gross Margin% | Strategic Leverage | Dependencies | Priority Rank | Phase | Confidence%
Chokepoint Intelligence Sprint | COO/Founder mid-market | $15-30K | 14 | 0 | 30 | One-time | 80 | Framework IP+data | None | 1 | Phase 1 | 85
DocuFlow Agent | Consultants/Legal/Coaches | $19-49/mo | 7 | 500 | 14 | Yes (MRR) | 70 | Usage data+lock-in | MVP build | 2 | Phase 1 | 75
Billing Leakage Engine | CFO Prof Services/SaaS | $20-40K+$5K/mo | 30 | 2000 | 60 | Yes (retainer) | 75 | Data integration | Client data access | 3 | Phase 1-2 | 70
Operator Track (Standard) | Professionals/Career changers | $1,000-1,500/person | 14 | 1000 | 90 | Cohort-based | 85 | Talent pipeline | First clients as proof | 4 | Phase 2 | 65
Operator Track (India) | Indian professionals | INR 75,000/person | 7 | 500 | 60 | Cohort-based | 90 | India pipeline | India network | 5 | Phase 2 | 60
Manufacturing OTIF Pilot | VP Ops Manufacturing | $95K | 60 | 5000 | 90 | Project+retainer | 55 | Vertical authority | Industry expertise | 6 | Phase 3 | 50
Logistics Fleet Pilot | VP Logistics | $80K | 60 | 5000 | 90 | Project+retainer | 55 | Vertical authority | Industry expertise | 7 | Phase 3 | 50
Professional Services Margin | Managing Partner | $110K | 60 | 5000 | 90 | Project+retainer | 60 | Vertical authority | Industry expertise | 8 | Phase 3 | 50
Insurance Claims Processing | Claims VP | $3-7/claim | 90 | 10000 | 120 | Yes (per-claim) | 65 | Data moat+underwriting | Carrier relationship | 9 | Phase 3 | 45
Banking Receivables Pilot | CFO/Treasury | $85K | 60 | 5000 | 90 | Project+retainer | 55 | Financial data | Banking compliance | 10 | Phase 3 | 45
Governance-as-a-Service | CISO/CTO Enterprise | $15-25K/yr | 90 | 20000 | 180 | Yes (annual) | 70 | Lock-in+compliance | Governance layer built | 11 | Phase 4 | 40
AINE Setup Fees | CTO/VP Eng | $10-50K+$5-20K/mo | 90 | 50000 | 180 | Yes (monthly) | 60 | Platform lock-in | Full AINE runtime | 12 | Phase 4 | 35
Compliance-as-a-Service | Chief Compliance Officer | $25-50K/yr | 120 | 30000 | 180 | Yes (annual) | 75 | Regulatory position | Compliance engine | 13 | Phase 4 | 35
Frankmax PIAR | Board/C-Suite | $50-100K/engagement | 120 | 25000 | 180 | Yes (annual) | 80 | Monopoly position | Case studies+credibility | 14 | Phase 4 | 30
Risk-Tier Certification | Enterprise Risk | $25K/enterprise | 90 | 15000 | 120 | Yes (annual) | 80 | Certification authority | Multiple implementations | 15 | Phase 4 | 30
UniVenture IP Licensing | Founders/Operators | $0.10-0.50/tx | 60 | 20000 | 180 | Yes (per-tx) | 85 | IP portfolio | IP stacks built | 16 | Phase 5 | 25
ORF Protocol Services | Enterprise/Institutional | $100K+/yr | 180 | 100000 | 365 | Yes (annual) | 70 | GDP-scale position | ORF kernel built | 17 | Phase 6 | 20
LPI Services | Government/Dynasty | $500K+/yr | 365 | 500000 | 730 | Yes (annual) | 60 | Sovereign position | Full LPI build | 18 | Phase 7 | 10
Underwriting Intelligence | Reinsurers | $100K/yr | 180 | 50000 | 365 | Yes (annual) | 80 | Data moat | 50K+ claims data | 19 | Phase 5 | 25
Construction Decisions Pilot | Project Director | $90K | 60 | 5000 | 90 | Project+retainer | 55 | Vertical authority | Industry expertise | 20 | Phase 3 | 45

## System Build Priority
System Name | Entity | Build Complexity(1-10) | Revenue Required? | Phase Needed | Build Duration(weeks) | Dependencies | Deferrable? | MVP Possible? | Priority Rank | Priority Color
DocuFlow Agent Runtime | Phase 1 | 3 | Y | Phase 1 | 2 | None | N | Y | 1 | GREEN
Chokepoint Framework Engine | Phase 1 | 2 | Y | Phase 1 | 1 | None | N | Y | 2 | GREEN
Website+CRM | Phase 1 | 2 | Y | Phase 1 | 1 | None | N | Y | 3 | GREEN
Billing Leakage Reconciliation | Phase 1-2 | 4 | Y | Phase 1-2 | 3 | None | N | Y | 4 | GREEN
Basic Agent Orchestration | Phase 2 | 5 | Y | Phase 2 | 4 | None | N | Y | 5 | GREEN
Telemetry/Logging | Phase 2 | 3 | N | Phase 2 | 2 | None | N | Y | 6 | GREEN
Operator Screening System | Phase 2 | 3 | Y | Phase 2 | 2 | None | N | Y | 7 | GREEN
Sprint Execution Engine | Phase 2 | 4 | Y | Phase 2 | 3 | None | N | Y | 8 | GREEN
Insurance Claims Agent | Phase 3 | 6 | Y | Phase 3 | 6 | Data integration | N | Y | 9 | YELLOW
Knowledge-Worker Copilot | Phase 3 | 6 | Y | Phase 3 | 6 | Agent orchestration | N | Y | 10 | YELLOW
Governance Engine | Phase 3-4 | 7 | N | Phase 3 | 8 | Logging system | N | Y | 11 | YELLOW
PEP Runtime | Phase 3 | 7 | N | Phase 3 | 8 | None | Y | Y | 12 | YELLOW
Agent Marketplace | Phase 4 | 7 | N | Phase 4 | 10 | Agent systems | Y | Y | 13 | YELLOW
Digital Identity System | Phase 4 | 6 | N | Phase 4 | 6 | None | Y | Y | 14 | YELLOW
Compliance Engine | Phase 4 | 6 | Y | Phase 4 | 6 | Governance | N | Y | 15 | YELLOW
Frankmax PIAR System | Phase 4 | 7 | Y | Phase 4 | 8 | Case studies | N | Y | 16 | YELLOW
Capital Allocation Engine | Phase 4 | 6 | N | Phase 4 | 6 | Financial data | Y | Y | 17 | YELLOW
Revenue Validation System | Phase 3 | 5 | Y | Phase 3 | 4 | Analytics | N | Y | 18 | YELLOW
Kill & Pivot Engine | Phase 3 | 4 | N | Phase 3 | 3 | Metrics | N | Y | 19 | YELLOW
AINE Registry | Phase 5 | 7 | N | Phase 5 | 8 | Identity | Y | N | 20 | RED
Cross-AINE Risk System | Phase 5 | 8 | N | Phase 5 | 10 | AINE registry | Y | N | 21 | RED
Failure Contagion Firewall | Phase 5 | 8 | N | Phase 5 | 10 | Risk system | Y | N | 22 | RED
Insurance Pool | Phase 5 | 9 | N | Phase 5 | 12 | Underwriting | Y | N | 23 | RED
Inter-AINE Contracts | Phase 5 | 7 | N | Phase 5 | 8 | Identity | Y | N | 24 | RED
ORF Kernel | Phase 6 | 8 | N | Phase 6 | 16 | Governance | Y | N | 25 | RED
Jurisdiction Partition | Phase 6 | 7 | N | Phase 6 | 8 | Legal | Y | N | 26 | RED
Portfolio Lifecycle | Phase 5 | 7 | N | Phase 5 | 8 | Capital engine | Y | N | 27 | RED
Resource Allocation | Phase 5 | 6 | N | Phase 5 | 6 | Metrics | Y | N | 28 | RED
Constitutional Amendment System | Phase 7+ | 9 | N | Phase 7+ | 16 | ORF kernel | Y | N | 29 | GRAY
Planetary Simulation | Phase 7+ | 10 | N | Phase 7+ | 52 | All systems | Y | N | 30 | GRAY
Imperial Intelligence Grid | Phase 7+ | 10 | N | Phase 7+ | 52 | All systems | Y | N | 31 | GRAY
Synthetic Economy Engine | Phase 7+ | 10 | N | Phase 7+ | 26 | ORF kernel | Y | N | 32 | GRAY
Machine Creativity Engine | Phase 7+ | 9 | N | Phase 7+ | 26 | All systems | Y | N | 33 | GRAY
Theory of Artificial Civilization | Never | 10 | N | Never | 99 | All systems | Y | N | 34 | GRAY
Private Military Cognition | Never | 10 | N | Never | 99 | Ethics | Y | N | 35 | GRAY

## Risk Register
ID | Risk Name | Category | Probability(1-5) | Impact(1-5) | Score(P×I) | Mitigation | Owner | Trigger Indicator | Phase Most Acute | Status
R1 | Zero revenue by Day 90 | Strategic | 3 | 5 | 15 | Daily sales pipeline review | Founder | No deal closures by Week 6 | Phase 1 | Active
R2 | Wrong vertical choice | Strategic | 3 | 4 | 12 | Vertical pivot framework | Founder | Vertical underperforms by Month 2 | Phase 1 | Active
R3 | Solo founder burnout | Operational | 4 | 5 | 20 | Operator hiring by Month 2 | Founder | Founder >60hr/week consistently | Phase 1-2 | Active
R4 | No product-market fit | Strategic | 3 | 5 | 15 | Customer discovery + iteration | Founder | Churn >20% or NPS <30 | Phase 1-2 | Active
R5 | AI model dependency | Technical | 2 | 4 | 8 | Multi-model orchestration layer | Tech Lead | Model provider outage >2hrs | Phase 2+ | Monitoring
R6 | Enterprise sales cycle too long | Financial | 3 | 4 | 12 | Focus on mid-market first | Sales Lead | Sales cycle >90 days | Phase 2 | Active
R7 | Operator quality variance | Operational | 3 | 3 | 9 | Screening + certification system | Ops Lead | Operator rework rate >10% | Phase 2+ | Active
R8 | Capital exhaustion | Financial | 3 | 5 | 15 | Cash flow dashboard + runway planning | Finance | Runway <60 days | Phase 1-3 | Active
R9 | Regulatory friction | Regulatory | 2 | 4 | 8 | Regulatory engagement + compliance layer | Legal | Regulator inquiry received | Phase 4+ | Monitoring
R10 | Competitive saturation | Strategic | 3 | 3 | 9 | Defensibility layer + IP moat | Founder | 3+ direct competitors launched | Phase 3+ | Monitoring
R11 | Data liability | Regulatory | 2 | 5 | 10 | Data governance + insurance layer | Compliance | Data breach or audit failure | Phase 3+ | Monitoring
R12 | Coordination collapse multi-agent | Technical | 2 | 4 | 8 | Orchestration framework testing | Tech Lead | Agent task failures >5% | Phase 3+ | Monitoring
R13 | Kill discipline failure | Operational | 3 | 5 | 15 | Kill protocol enforcement + metrics | Founder | Ventures running >90 days past exit | Phase 1+ | Critical
R14 | Architecture seduction | Strategic | 4 | 4 | 16 | Founder discipline + PCI enforcement | Founder | Building unrequested features | Phase 1-2 | Critical
R15 | Governance erosion under pressure | Operational | 3 | 4 | 12 | Written governance standards | Founder | Exception approvals >1/week | Phase 2+ | Active
R16 | Promotion inflation | Operational | 3 | 3 | 9 | Metrics-based promotion criteria | Ops Lead | Operator tenure <6mo at promotion | Phase 2+ | Active
R17 | Over-engineering before market fit | Strategic | 4 | 4 | 16 | MVP-first discipline | Tech Lead | Build cycle >4 weeks without revenue | Phase 1-2 | Critical
R18 | Technology obsolescence | Technical | 2 | 3 | 6 | Modular architecture + provider-agnostic | Tech Lead | New model release >2x capabilities | Phase 3+ | Monitoring
R19 | Margin collapse | Financial | 2 | 4 | 8 | Margin floor enforcement | Finance | Gross margin <50% on core products | Phase 2+ | Active
R20 | Founder ego override of PCI | Operational | 3 | 5 | 15 | External governance board | Board | PCI exception bypassed | Phase 1+ | Critical

## Financial Model
EXECUTION BLUEPRINT - FINANCIAL MODEL
Category | Jan Y1 | Feb Y1 | Mar Y1 | Apr Y1 | May Y1 | Jun Y1 | Jul Y1 | Aug Y1 | Sep Y1 | Oct Y1 | Nov Y1 | Dec Y1
REVENUE
DocuFlow MRR | 0 | 2000 | 4000 | 5000 | 6000 | 7000 | 8000 | 9000 | 10000 | 11000 | 12000 | 13000
Chokepoint Sprints | 20000 | 20000 | 20000 | 15000 | 0 | 25000 | 0 | 0 | 0 | 20000 | 0 | 0
Billing Leakage | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Operator Track | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
Insurance Claims | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 12000 | 15000 | 18000 | 20000 | 22000
Market Wedge Pilots | 0 | 0 | 0 | 0 | 10000 | 15000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
TOTAL REVENUE | 20000 | 22000 | 29000 | 55000 | 51000 | 82000 | 71000 | 76000 | 80000 | 104000 | 87000 | 90000
Tools & Infrastructure | 500 | 500 | 500 | 800 | 800 | 800 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500
Cloud Compute | 200 | 200 | 300 | 500 | 500 | 500 | 800 | 800 | 800 | 1000 | 1000 | 1000
Marketing | 500 | 1000 | 1000 | 1500 | 1500 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Contractor/Operator Comp | 0 | 0 | 0 | 5000 | 5000 | 5000 | 8000 | 10000 | 12000 | 15000 | 15000 | 15000
Legal/Compliance | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Travel/Meetings | 500 | 500 | 500 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
TOTAL COSTS | 2200 | 2700 | 2800 | 8800 | 8800 | 9300 | 12600 | 14600 | 16600 | 19800 | 19800 | 19800
GROSS PROFIT | 17800 | 19300 | 26200 | 46200 | 42200 | 72700 | 58400 | 61400 | 63400 | 84200 | 67200 | 70200
Gross Margin % | 89% | 87.73% | 90.34% | 84% | 82.75% | 88.66% | 82.25% | 80.79% | 79.25% | 80.96% | 77.24% | 78%
CUMULATIVE CASH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ASSUMPTIONS (Blue = Input Cells)
DocuFlow growth rate/month | 20%
Chokepoint deal size avg | 20000
Billing Leakage deal size | 30000
Operator Track cohort size | 30
Insurance claims per month (starting Month 7) | 2000

## Metrics Dashboard
KPI Name | Target (Monthly) | Week 1-4 Actuals | Month Total | vs Target | Status
Revenue | 10000 |  | 0 | 0% | RED
New Customers | 5 |  | 0 | 0% | RED
Discovery Conversations | 20 |  | 0 | 0% | RED
Proposals Sent | 3 |  | 0 | 0% | RED
Deals Closed | 1 |  | 0 | 0% | RED
DocuFlow Users | 10 |  | 0 | 0% | RED
Operator Pipeline | 10 |  | 0 | 0% | RED
Agent Tasks Completed | 100 |  | 0 | 0% | RED
Client Retention % | 95% |  | 0 | 0% | RED
Gross Margin % | 70% |  | 0 | 0% | RED
Cash Position | 50000 |  | 0 | 0% | RED
Burn Rate | 5000 |  | 0 | 0% | RED